## Project Estimation
| Project Estimering | [5 empty] | Project Periode
|  | 67 | 81 | 143 |  |  |  |  | Min
|  | O | M | P | Notes |  | 2023-12-03 | Søn | 4 | 1
| 1. Project Setup | 1 | 2 | 8 | - Install Node.js and set up the development environment - Create a new React Native project without Expo - Configure TypeScript |  | 2023-12-04 | Man | 5 | 2
| 2. Design and theme | 3 | 4 | 12 | - standard guidelines provided by Apple and Google. |  | 2023-12-05 | Tir | 5 | 3
| 3. Splash Screen | 3 | 4 | 7 | - Design and implement the splash screen - Ensure it fades in and transitions to the appropriate screen |  | 2023-12-06 | Ons | 5 | 4
| 4. Login Screen | 7 | 8 | 14 | - Implement social login methods (Facebook, Google) - Handle login errors and display dialogs - Navigate to the Chat Rooms screen upon successful login |  | 2023-12-07 | Tho | 5 | 5
| 5. Chat Rooms | 9 | 10 | 14 | - Fetch and display a list of available rooms - Sort the list by the newest message - Implement pull-to-refresh functionality - Navigate to the Send and Receive screen upon selecting a room |  | 2023-12-08 | Fre | 5 | 6
| 6. Send and Receive Messages | 9 | 10 | 14 | - Load the last 50 messages when opening a chat room - Implement infinite scrolling for more messages - Implement the input field for sending messages - Display messages with sender details and date |  | 2023-12-09 | Lør | 0
| 7. Push Functionality | 7 | 8 | 16 | - Prompt user for notification preferences - Implement Firebase Cloud Messaging (FCM) for push notifications - Implement deep linking for direct navigation to rooms/messages |  | 2023-12-10 | Søn | 0
| 8. Upload Images to Chat Room | 5 | 6 | 12 | - Implement image upload from camera and gallery - Display uploaded images in the chat room |  | 2023-12-11 | Man | 5 | 7
| 9. Testing and Debugging | 8 | 9 | 14 | - Test each feature and fix any issues - Ensure the app functions correctly on both Android and "iOS" |  | 2023-12-12 | Tir | 5 | 8
| 10. Documentation and Clean-Up | 5 | 6 | 12 | - Document the code, especially complex or critical sections - Clean up any unnecessary code or files |  | 2023-12-13 | Ons | 5 | 9
| 11. Buffer Time | 10 | 14 | 20 | - Account for unforeseen challenges, debugging, and additional testing |  | 2023-12-14 | Tho | 5 | 10
| Total Estimated Hours: | 67 | 81 | 143 |  |  | 2023-12-15 | Fre | 5 | 11
[7 empty] | 2023-12-16 | Lør | 0
| 100% af projeketet færdigt | [5 empty] | 2023-12-17 | Søn | 0
[7 empty] | 2023-12-18 | Man | 5 | 12
| Best | 67 | O |  |  |  | 2023-12-19 | Tir | 5 | 13
| Most likely | 81 | M | [5 empty] | 64
| Worst | 143 | P
(PERT): E = (o + 4m + p ) / 6
| Mean | 89
| The Standard Deviation | 12.6667 | (p - o)/6
| 68% lower | 76.3333
| 68% upper | 101.6667
|  | hours | %
| Inversion by | 90% | 64
| Norm inversion | 105.233 | 2.421%
60% af projeketet færdigt
| 60% | 40.2 | 48.6 | 85.8
| Best | 40.2 | O
| Most likely | 48.6 | M
| Worst | 85.8 | P
(PERT): E = (o + 4m + p ) / 6
| Mean | 53.4
| The Standard Deviation | 7.6 | (p - o)/6
| 68% lower | 45.8
| 68% upper | 61
|  | hours | %
| Inversion by | 90% | 64
| Norm inversion | 63.1398 | 91.85%
Min tidsperiode
[6 empty] | 100% | 60%
| 100% |  | 60%
0.01% | 41.8925 | 3.1251e-05 | 25.1355 | 5.2085e-05 |  | 64 | 0.019846
0.05% | 47.32 | 0.0001403 | 28.392 | 0.00023384 |  | 64 | 0.019846
0.1% | 49.8571 | 0.00026582 | 29.9142 | 0.00044304 |  | 64 | 0.019846
0.2% | 52.5433 | 0.00050054 | 31.526 | 0.00083424 |  | 64 | 0.019846
0.4% | 55.4071 | 0.00093529 | 33.2443 | 0.0015588 |  | 64 | 0.019846
0.8% | 58.4871 | 0.0017305 | 35.0922 | 0.0028842 |  | 64 | 0.019846
1% | 59.5329 | 0.0021041 | 35.7198 | 0.0035069 |  | 64 | 0.019846
2% | 62.9858 | 0.0038225 | 37.7915 | 0.0063708 |  | 64 | 0.019846
3% | 65.1766 | 0.0053717 | 39.106 | 0.0089529 |  | 64 | 0.019846
4% | 66.8246 | 0.0068032 | 40.0948 | 0.011339 |  | 64 | 0.019846
5% | 68.1652 | 0.0081423 | 40.8991 | 0.01357 |  | 64 | 0.019846
10% | 72.767 | 0.013855 | 43.6602 | 0.023092 |  | 64 | 0.019846
15% | 75.8718 | 0.018407 | 45.5231 | 0.030679 |  | 64 | 0.019846
20% | 78.3395 | 0.022102 | 47.0037 | 0.036837 |  | 64 | 0.019846
25% | 80.4565 | 0.025088 | 48.2739 | 0.041813 |  | 64 | 0.019846
30% | 82.3576 | 0.027449 | 49.4146 | 0.045749 |  | 64 | 0.019846
35% | 84.1193 | 0.029242 | 50.4716 | 0.048737 |  | 64 | 0.019846
40% | 85.7909 | 0.030501 | 51.4746 | 0.050835 |  | 64 | 0.019846
45% | 87.4083 | 0.031248 | 52.445 | 0.05208 |  | 64 | 0.019846
50% | 89 | 0.031495 | 53.4 | 0.052492 |  | 64 | 0.019846
55% | 90.5917 | 0.031248 | 54.355 | 0.05208 |  | 64 | 0.019846
60% | 92.2091 | 0.030501 | 55.3254 | 0.050835 |  | 64 | 0.019846
65% | 93.8807 | 0.029242 | 56.3284 | 0.048737 |  | 64 | 0.019846
70% | 95.6424 | 0.027449 | 57.3854 | 0.045749 |  | 64 | 0.019846
75% | 97.5435 | 0.025088 | 58.5261 | 0.041813 |  | 64 | 0.019846
80% | 99.6605 | 0.022102 | 59.7963 | 0.036837 |  | 64 | 0.019846
85% | 102.1282 | 0.018407 | 61.2769 | 0.030679 |  | 64 | 0.019846
90% | 105.233 | 0.013855 | 63.1398 | 0.023092 |  | 64 | 0.019846
95% | 109.8348 | 0.0081423 | 65.9009 | 0.01357 |  | 64 | 0.019846
99% | 118.4671 | 0.0021041 | 71.0802 | 0.0035069 |  | 64 | 0.019846 | 1%
99.2% | 119.5129 | 0.0017305 | 71.7078 | 0.0028842 |  | 64 | 0.019846 | 0.8%
99.6% | 122.5929 | 0.00093529 | 73.5557 | 0.0015588 |  | 64 | 0.019846 | 0.4%
99.8% | 125.4567 | 0.00050054 | 75.274 | 0.00083424 |  | 64 | 0.019846 | 0.2%
99.9% | 128.1429 | 0.00026582 | 76.8858 | 0.00044304 |  | 64 | 0.019846 | 0.1%
99.95% | 130.68 | 0.0001403 | 78.408 | 0.00023384 |  | 64 | 0.019846 | 0.05%
99.99% | 136.1075 | 3.1251e-05 | 81.6645 | 5.2085e-05 |  | 64 | 0.019846 | 0.01%

## Log
Hours sum | Date | Start clock | End clock | Hours | Log | Regex filter clock |  |  |  | Convert to hours
6 | 2023-12-03 | 10:00 | 16:00 | 6 | Estimate the project timeline and objectives | 10 | 00 | 16 | 00 | 6 | 0 | 6
11.1167 | 2023-12-04 | 06:30 | 11:37 | 5.1167 | Trying to get React-Native to work on Linux | 06 | 30 | 11 | 37 | 5 | 7 | 5.1167
13.4833 | 2023-12-04 | 10:38 | 12:30 | 2.3667 | Merge pull request #1 from Flakvard/init_react-native | 10 | 38 | 12 | 30 | 2 | 22 | 2.3667
13.8167 | 2023-12-04 | 13:40 | 14:09 | 0.33333 | Getting the app structure and layout done | 13 | 40 | 14 | 09 | 0 | 20 | 0.33333
14.8167 | 2023-12-04 | 15:15 | 16:15 | 1 | Merge pull request #2 from Flakvard/app-structure | 15 | 15 | 16 | 15 | 1 | 0 | 1
19.5167 | 2023-12-04 | 20:18 | 24:00 | 4.7 | Theme and standard UI componants | 20 | 18 | 24 | 00 | 4 | 42 | 4.7
24.1833 | 2023-12-05 | 12:20 | 16:10 | 4.6667 | Theme and standard UI componants | 12 | 20 | 16 | 10 | 4 | 40 | 4.6667
24.1833 | 2023-12-06 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
24.1833 | 2023-12-07 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
24.1833 | 2023-12-08 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
25.5167 | 2023-12-09 | 22:00 | 23:20 | 1.3333 | Colors to Theme | 22 | 00 | 23 | 20 | 1 | 20 | 1.3333
27.5167 | 2023-12-10 | 10:00 | 12:00 | 2 | Gimp (image editor) icon and logo | 10 | 00 | 12 | 00 | 2 | 0 | 2
30.5833 | 2023-12-11 | 12:10 | 15:14 | 3.0667 | Icon og splash screen | 12 | 10 | 15 | 14 | 3 | 4 | 3.0667
31.3333 | 2023-12-11 | 22:00 | 22:45 | 0.75 | Merge pull request #3 from Flakvard/UI-Components-lib | 22 | 00 | 22 | 45 | 0 | 45 | 0.75
33.4667 | 2023-12-12 | 00:00 | 02:08 | 2.1333 | Navigation root and auth feature | 00 | 00 | 02 | 08 | 2 | 8 | 2.1333
34.0167 | 2023-12-12 | 12:00 | 12:33 | 0.55 | Merge pull request #4 from Flakvard/navigation | 12 | 00 | 12 | 33 | 0 | 33 | 0.55
36.1833 | 2023-12-12 | 12:50 | 14:45 | 2.1667 | State Management with Redux | 12 | 50 | 14 | 45 | 2 | 10 | 2.1667
36.1833 | 2023-12-13 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
36.1833 | 2023-12-14 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
36.1833 | 2023-12-15 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
36.1833 | 2023-12-16 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
38.25 | 2023-12-17 | 22:26 | 24:30 | 2.0667 | State Management with Redux | 22 | 26 | 24 | 30 | 2 | 4 | 2.0667
39.65 | 2023-12-18 | 23:30 | 24:54 | 1.4 | Working State Management with redux | 23 | 30 | 24 | 54 | 1 | 24 | 1.4
41.7333 | 2023-12-19 | 00:55 | 02:14 | 2.0833 | Message chat UI & structure + status | 00 | 55 | 02 | 14 | 2 | 5 | 2.0833
44.4667 | 2023-12-19 | 21:16 | 23:10 | 2.7333 | Message chat UI and structure, create img + msg functions | 21 | 16 | 23 | 10 | 2 | 44 | 2.7333
46.5833 | 2023-12-20 | 00:50 | 02:57 | 2.1167 | Message chat UI, toolbar + create img + msg functions and img fullscreen | 00 | 50 | 02 | 57 | 2 | 7 | 2.1167
46.5833 | 2023-12-21 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
46.5833 | 2023-12-22 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
46.5833 | 2023-12-23 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
46.5833 | 2023-12-24 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
46.5833 | 2023-12-25 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
46.5833 | 2023-12-26 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
48.0833 | 2023-12-27 | 22:00 | 23:30 | 1.5 | Message camera upload Grid | 22 | 00 | 23 | 30 | 1 | 30 | 1.5
48.7833 | 2023-12-28 | 23:18 | 24:00 | 0.7 | Message camera upload Grid | 23 | 18 | 24 | 00 | 0 | 42 | 0.7
48.95 | 2023-12-29 | 23:50 | 24:00 | 0.16667 | Message camera upload Grid | 23 | 50 | 24 | 00 | 0 | 10 | 0.16667
50.2667 | 2023-12-30 | 00:00 | 01:19 | 1.3167 | Message camera upload Grid | 00 | 00 | 01 | 19 | 1 | 19 | 1.3167
50.4833 | 2023-12-30 | 01:20 | 01:33 | 0.21667 | Google sheet clean up and reorganisation | 01 | 20 | 01 | 33 | 0 | 13 | 0.21667
52.5333 | 2023-12-31 | 22:57 | 24:00 | 2.05 |  | 22 | 57 | 24 | 00 | 2 | 3 | 2.05
52.5333 | 2024-01-01 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
53.5333 | 2024-01-02 | 12:00 | 13:00 | 1 | Access Camera images Android: rn-fetch-blob package | 12 | 00 | 13 | 00 | 1 | 0 | 1
58.5333 | 2024-01-03 | 10:00 | 15:00 | 5 | Access Camera images Android: image-picker & rn-fetch-blob package | 10 | 00 | 15 | 00 | 5 | 0 | 5
61.2833 | 2024-01-03 | 18:10 | 20:55 | 2.75 | Access Camera images Android camera-rool package (https://github.com/react-native-cameraroll/react-native-cameraroll) | 18 | 10 | 20 | 55 | 2 | 45 | 2.75
63.5667 | 2024-01-04 | 08:30 | 10:47 | 2.2833 | Access Camera images Android camera-rool package working | 08 | 30 | 10 | 47 | 2 | 17 | 2.2833
64.6667 | 2024-01-04 | 10:48 | 11:54 | 1.1 | Camera images pagenation | 10 | 48 | 11 | 54 | 1 | 6 | 1.1
64.7667 | 2024-01-04 | 11:54 | 12:30 | 0.1 | Camera images sending images | 11 | 54 | 12 | 30 | 0 | 6 | 0.1
68.2667 | 2024-01-04 | 12:30 | 15:00 | 3.5 | Messaging Container, layout and Keyboard state | 12 | 30 | 15 | 00 | 3 | 30 | 3.5
75.5167 | 2024-01-05 | 08:45 | 15:30 | 7.25 | Messaging Container, layout and Keyboard state | 08 | 45 | 15 | 30 | 7 | 15 | 7.25
78.0167 | 2024-01-05 | 13:00 | 15:30 | 2.5 | Messaging Container animation | 13 | 00 | 15 | 30 | 2 | 30 | 2.5
79.4 | 2024-01-05 | 21:30 | 22:53 | 1.3833 | Messaging Container animation removed/discarded | 21 | 30 | 22 | 53 | 1 | 23 | 1.3833
80.15 | 2024-01-05 | 23:00 | 23:45 | 0.75 | Fix message sending via keyboard | 23 | 00 | 23 | 45 | 0 | 45 | 0.75
80.4 | 2024-01-05 | 23:45 | 24:00 | 0.25 | Fix sending receiving message styling | 23 | 45 | 24 | 00 | 0 | 15 | 0.25
81.65 | 2024-01-06 | 00:00 | 01:15 | 1.25 | Fix sending receiving message styling | 00 | 00 | 01 | 15 | 1 | 15 | 1.25
82.4 | 2024-01-06 | 01:15 | 02:07 | 0.75 | Seed 50 messages and scroll to load more messages | 01 | 15 | 02 | 07 | 0 | 45 | 0.75
83.25 | 2024-01-06 | 02:07 | 02:58 | 0.85 | Merge pull request #5 from Flakvard/Message-UI | 02 | 07 | 02 | 58 | 0 | 51 | 0.85
84.2667 | 2024-01-06 | 02:58 | 03:59 | 1.0167 | RoomList and RoomListItem with dummy contacts via API | 02 | 58 | 03 | 59 | 1 | 1 | 1.0167
86.2667 | 2024-01-06 | 14:00 | 16:00 | 2 | RoomList and RoomListItem with dummy contacts via API | 14 | 00 | 16 | 00 | 2 | 0 | 2
86.5667 | 2024-01-06 | 22:42 | 23:36 | 0.3 | Merge pull request #6 from Flakvard/ChatRoom-UI | 22 | 42 | 23 | 36 | 0 | 18 | 0.3
86.9667 | 2024-01-06 | 23:36 | 24:00 | 0.4 | Profile-UI, ContactThumbnail, DetailListItem + fixed navigation | 23 | 36 | 24 | 00 | 0 | 24 | 0.4
88.5667 | 2024-01-07 | 00:00 | 01:36 | 1.6 | Merge pull request #7 from Flakvard/Profile-UI | 00 | 00 | 01 | 36 | 1 | 36 | 1.6
90.9667 | 2024-01-07 | 01:36 | 03:00 | 2.4 | User UI and Options | 01 | 36 | 03 | 00 | 2 | 24 | 2.4
94.9667 | 2024-01-07 | 03:00 | 07:00 | 4 | Rewrite navigation and stack, Theme applied everywhere | 03 | 00 | 07 | 00 | 4 | 0 | 4
97.35 | 2024-01-07 | 10:03 | 12:26 | 2.3833 | Merge pull request #8 from Flakvard/User-UI | 10 | 03 | 12 | 26 | 2 | 23 | 2.3833
98.5167 | 2024-01-07 | 12:03 | 13:13 | 1.1667 | Clean up and docs | 12 | 03 | 13 | 13 | 1 | 10 | 1.1667
101.3 | 2024-01-07 | 13:13 | 15:00 | 2.7833 | Merge pull request #9 from Flakvard/Clean-up | 13 | 13 | 15 | 00 | 2 | 47 | 2.7833
101.3 | 2024-01-08 | 00:00 | 00:00 | 0 |  | 00 | 00 | 00 | 00 | 0 | 0 | 0
Formulas:
Date = [Date, row above]+1

## Stats
3.8571
21
Burndown | Burndown estimate | Burndown | Total hours each day | Comitted | Commit hours | Completed hours
2023-12-03 | 81 | 75 | 6 | 4 | 4 | 6
2023-12-04 | 77.1429 | 61.4833 | 13.5167 | 5 | 9 | 19.5167
2023-12-05 | 73.2857 | 56.8167 | 4.6667 | 5 | 14 | 24.1833
2023-12-06 | 69.4286 | 56.8167 | 0 | 5 | 19 | 24.1833
2023-12-07 | 65.5714 | 56.8167 | 0 | 5 | 24 | 24.1833
2023-12-08 | 61.7143 | 56.8167 | 0 | 5 | 29 | 24.1833
2023-12-09 | 61.7143 | 55.4833 | 1.3333 | 0 | 29 | 25.5167
2023-12-10 | 61.7143 | 53.4833 | 2 | 0 | 29 | 27.5167
2023-12-11 | 57.8571 | 49.6667 | 3.8167 | 5 | 34 | 31.3333
2023-12-12 | 54 | 44.8167 | 4.85 | 5 | 39 | 36.1833
2023-12-13 | 50.1429 | 44.8167 | 0 | 5 | 44 | 36.1833
2023-12-14 | 46.2857 | 44.8167 | 0 | 5 | 49 | 36.1833
2023-12-15 | 42.4286 | 44.8167 | 0 | 5 | 54 | 36.1833
2023-12-16 | 42.4286 | 44.8167 | 0 | 0 | 54 | 36.1833
2023-12-17 | 42.4286 | 42.75 | 2.0667 | 0 | 54 | 38.25
2023-12-18 | 38.5714 | 41.35 | 1.4 | 5 | 59 | 39.65
2023-12-19 | 34.7143 | 36.5333 | 4.8167 | 5 | 64 | 44.4667
2023-12-20 | 30.8571 | 34.4167 | 2.1167 | 5 | 69 | 46.5833
2023-12-21 | 30.8571 | 34.4167 | 0 | 0 | 69 | 46.5833
2023-12-22 | 30.8571 | 34.4167 | 0 | 0 | 69 | 46.5833
2023-12-23 | 30.8571 | 34.4167 | 0 | 0 | 69 | 46.5833
2023-12-24 | 30.8571 | 34.4167 | 0 | 0 | 69 | 46.5833
2023-12-25 | 30.8571 | 34.4167 | 0 | 0 | 69 | 46.5833
2023-12-26 | 30.8571 | 34.4167 | 0 | 0 | 69 | 46.5833
2023-12-27 | 27 | 32.9167 | 1.5 | 0 | 69 | 48.0833
2023-12-28 | 23.1429 | 32.2167 | 0.7 | 0 | 69 | 48.7833
2023-12-29 | 19.2857 | 32.05 | 0.16667 | 0 | 69 | 48.95
2023-12-30 | 19.2857 | 30.5167 | 1.5333 | 0 | 69 | 50.4833
2023-12-31 | 19.2857 | 28.4667 | 2.05 | 0 | 69 | 52.5333
2024-01-01 | 19.2857 | 28.4667 | 0 | 0 | 69 | 52.5333
2024-01-02 | 15.4286 | 27.4667 | 1 | 5 | 74 | 53.5333
2024-01-03 | 11.5714 | 19.7167 | 7.75 | 5 | 79 | 61.2833 | 0
2024-01-04 | 7.7143 | 12.7333 | 6.9833 | 5 | 84 | 68.2667
2024-01-05 | 3.8571 | 0.6 | 12.1333 | 5 | 89 | 80.4
2024-01-06 | 3.8571 | -5.9667 | 6.5667 | 0 | 89 | 86.9667
2024-01-07 | 3.8571 | -20.3 | 14.3333 | 0 | 89 | 101.3
2024-01-08 | 0 | -20.3 | 0 | 0 | 89 | 101.3
Formulas:
Burndown = [Burndown, row above]+1